## Slide 1: LEARNING PLAN
ACTIVITY NAME | PURPOSE / FOCUS AREA | Deliverables | CANVAS CATEGORY | TIMING | OWNERS
Identify Stakeholders | Identify business lines, technology teams, etc. to be served as part of this project | Market (May 28th) | TARGET AUDIENCES | 5/16 – 5/25 | Ziad Asim
Plan SME Interviews (Interviewee List & Interview Scripts) | Discover Business Processes & Procedures | Interview List (w/Status) Interview Script(s) (May 28th) | PROBLEM | 5/22 – 5/28 | Stacie/Shahid Afzal/Ziad Asim/Jason
Journey Map | Detailed Task Sheet, milestones & dates, Progress Charts. | Journey Map (May 28th) | Project Management | 5/29 – 6/8 | Stacie/Shahid Afzal/Ziad Asim/Jason/Awais
Conduct SME Interviews | Execute Interview Scripts |  | PROBLEM | 5/29 – 6/8 | Stacie/Shahid Afzal/Ziad Asim/Jason
Identify Process Collateral & Documentation | Identify & Define Mechanism(s) to Document Business Processes |  | SOLUTION | 5/22 – 5/28 | Stacie/Rebecca Green
Explore Collaboration Tools at US Bank | Identify As Is & To Be Collaboration Technology State at US Bank |  | SOLUTION | 5/24 – 6/1 | Awais Sultan/Stacie
Define Solution Position & Pitch | Determine how the collaboration solution will be positioned and marketed across the enterprise | SOLUTION & VALUE PROP Synthesis Canvas (v2) Learning Plan (v2) Jun 11th DESIRABILITY Problem Pitch Deck Problem Pitch Learning Doc Jun 25th | SOLUTION | 6/4 – 6/8 | Stacie/Shahid Afzal/Awais Sultan
Define Support Team Placement & Structure | Devise Support Team Structure and Enterprise Placement for Support Team |  | SOLUTION | 6/7 – 6/12 | Stacie/Awais Sultan
Quantify Value Proposition | Identify tangible return s on investment for the business lines that this initiative will serve | Prototype Model (v1) Canvas (v3) Journey Map (Future State) Learning Plan (v3) July 16th | VALUE PROPOSITIONS | 6/13 – 6/15 | Jason/Stacie/Ziad Asim
PROJECT: Business & Technology Bridge​
v1