## Sheet1
Data Strategy | Enterprise Data Strategy (ELZ) | Use Cassandra (No SQL DB) as DB and data will be transferred from Cassandra to Offline 360 on daily basis and reports will run on Offline360. Reporting tools will call APIs to get data. There is also online 360 for near to real time data access bu tha will nobe utilized here. Data read/write from Cassandra will be through GRAPHQL APIs developed by WISE/EASE team Cassandra is On-Prem currently Cassandra in GCP by Q1 2021 Cassandra in AWS by Q2/Q3 2021 | Michael L Palmer (Product Owner) Guddanti, Seshu K Gopinathan Nair, Bijulal (Manages Cassandra) Shiva Sood (WM Data Architect) Balu (WISE/EASE GraphQL APIs for Cassandra)
| IS Data Strategy | Application data is stored in RDBMS (SQL server in case of BPM). Data will be transferred to ODS (on daily basis)/ DataMart (DataMart is Similar to Online360). Reports will run through ODS/ DataMart. ETL transfer service is managed by IS Data team. Down the road they have a plan to replace their components with corresponding ELZ components. | Zain Diwan (Product Owner) Prakash Udhayakumar Sampath Kumar S Malladi (Architect)
| SQL Server RDBMS (BPM Current Data Strategy) | Most of the BPM apps save data in SQL server. Most of the reports directly through SQL server data.
| Notes: | 1. Data Strategy is for Application data and not covering Product DB. Product DB will use DB type as suggested by Vendor. Application data should contain all data it needs in its own db and should prevent joins/db links/views with Product db.
2. Data from other DB sources, system of records should be through relevant APIs. DB joins, db links, db views should be prevented across dbs.
3. Application db should maintian data to support transactions, but should no become data for reports or system of record. Transactional database is arranged in a certain way and normally follow object oriented db model maintaing business objects used for business transactions. Whereas DB for reports should be arranged in altogether different way (normalized relational model) to support report queries.
4. In ELZ strategy, offline 360 can act as archival db. Data should be transferrable back to Cassandra if needed for some rare special cases.
Red colored items in the table, are discussable items that may need to be sorted out.
App Name | Current Infrastructure | Current Data Strategy | Target Infrastructure | Target Data Strategy | Steps
Cassandra POC | React/Java Internal Cloud BPM On-Prem | N/A | React/Java Internal Cloud BPM On-Prem | ELZ | 1. Perform POC. a- Rashid is setting up meeting with Cognizant to get POC done with their help. b- Cassandra Database will be created following the tables that are already created in SQL Server for Unfied Onboarding. c- GraphQL APIs will be created through WISE/EASE team. d- Make UO applicaion work with Cassandra db. It could be replica of UO applicaion to not effect UO releases
Unified OnBoarding | React/Java Internal Cloud BPM On-Prem | SQL Server RDBMS | AWS | ELZ | 1. DB Model. DB Model can be created after looking at Unified Onboarding requirements, FSAO, ITAO and IAS databases. DB Model can be shared with ELZ team and they will suggest/approve db model. 3. Evaluate to Reuse POC artifacts, especially DB model. 4. Get GraphQL APIs created from WISE/EASE team to read/write to Cassandra through App. 5. Evaluate how much updates are needed in APP from DB queries to GraphQL API calls and accordingly find out a repeatable method to perform this step. 6. This is a new app so previous data transfer is not needed to new db. 7. Should we complete this app migration to new DataStrategy before its migration to AWS.
ITAO | On-Prem | SQL Server RDBMS | AWS | ELZ | 1. Evaluate a way to be able to auto-convert current tables to Cassandra tables. Should we split tables to UO/Application Db model or replicate AS-IS tables to Cassandra? 2. Update app and replace db queries with GraphQL API calls. Evaluate a repeatable method for this step. Will there be any UI upgrade, using React/Angular UO app and what about employee task screens? 3. Evaluate a way to transfer data for ongoing events to new db. 4. Reports should be through offline 360. 5. External apps should update endpoints, if needed, to get data from new source. 7. This effort can be tied up with migration to AWS Cloud OR Should we complete this app migration to new DataStrategy before its migration to AWS.
FSAO | React/Java Internal Cloud BPM On-Prem | IS Data Strategy (SQL Server - ODS - Reporting tools) | AWS | ELZ | 1. Evaluate if data strategy should be changed from IS Data Strategy to ELZ. 2. Evaluate a way to be able to auto-convert current tables to Cassandra tables. 3. Update app and replace db queries with GraphQL API calls. Evaluate a repeatable method for this step. 4. Evaluate a way to transfer data for ongoing events to new db. 5. Reports should be through offline 360. 6. External apps should update endpoints, if needed, to get data from new source. 7. This effort can be tied up with migration to AWS Cloud OR Should we complete this app migration to new DataStrategy before its migration to AWS.
CTAO | On-Prem | IS Data Strategy (SQL Server - DataMart - Reporting tools) | AWS | ELZ | 1. Evaluate if data strategy should be changed from IS Data Strategy to ELZ. 2. Evaluate a way to be able to auto-convert current tables to Cassandra tables. Should we split tables to UO/Application Db model or replicate AS-IS tables to Cassandra? 3. Update app and replace db queries with GraphQL API calls. Evaluate a repeatable method for this step. Will there be any UI upgrade, using React/Angular UO app and what about employee task screens? 4. Evaluate a way to transfer data for ongoing events to new db. 5. Reports should be through offline 360. 6. External apps should update endpoints, if needed, to get data from new source. 7. This effort can be tied up with migration to AWS Cloud OR Should we complete this app migration to new DataStrategy before its migration to AWS.
IAS, PTAO, PTAM, USBi, Entrata, LN Non-Fee Apps, CCWIP, SASR | On-Prem | SQL Server RDBMS | AWS | ELZ | 1. Evaluate a way to be able to auto-convert current tables to Cassandra tables. Should we split tables to UO/Application Db model or replicate AS-IS tables to Cassandra? 2. Update app and replace db queries with GraphQL API calls. Evaluate a repeatable method for this step. Will there be any UI upgrade, using React/Angular UO app and what about employee task screens? 3. Evaluate a way to transfer data for ongoing events to new db. 4. Reports should be through offline 360. 5. External apps should update endpoints, if needed, to get data from new source. 7. This effort can be tied up with migration to AWS Cloud OR Should we complete this app migration to new DataStrategy before its migration to AWS. 8. These apps can be moved to new infra, data structure as a whole versus just focusing on specific onboarding screens (like only client onboarding screens)